## Slide 1: What is a project
  Unique a set of coordinated and controlled activities with clearly defined start and finish dates, undertaken to achieve an objective conforming to specific requirements
  A Project is a planned set of activities
  A Project has a scope
  A Project has time, cost, quality and resource constraints
  A Project is temporary

## Slide 2: Q1. Which is not a project?
  Implementation of new IT system
  Launch of a new product line
  Tracking of ongoing maintenance at a power plant
  Rebranding an established product
  Train employees on new system
Source: APP 2015/2016, 2011 KZN Hospital Survey
Notes: Source: ABSA SME Index 2015

## Slide 3: The Operational Environment
CEO
Finance
Marketing
R&D
IT
Production
HR
New product
New leave system
Training
Project office

## Slide 4: Role of the project manager
Source from RISHEN!
The project manager must manage relationships between…
Within the project team
Between project team and functional organisation
Between the project team and senior management
Between the project team and the customer’s organization, whether an internal or external organization.
Notes: Remember to add sources

## Slide 5: Activity 1:
“Project management is designed to make better use of existing resources by getting work to flow horizontally as well as vertically within the company.”
With the aid of a diagram, explain how the typical bureaucratic company is structured in terms of both management and functional divisions. How does project management principles assist these operational islands to work together towards achieving project objectives?
15 min

## Slide 6: Driving forces for project management
Capital projects
Customer expectations
Competitiveness
Executive understanding
New project development
Efficiency and effectiveness
SURVIVAL

## Slide 7: Reasons for project planning
Reasons for project planning
To eliminate or reduce uncertainty
To improve efficiency of the operation
To obtain a better understanding of the objectives
To provide a basis for monitoring and controlling work
Components of planning
1
2
3
4
5
6
7
Objective
8
9
Programme
Schedule
Budget
Forecast
Organisation
Policy
Procedure
Standard
Notes: 1. Objective: a goal, target, or quota to be achieved by a certain time
2. Program: the strategy to be followed and major actions to be taken in order to
3. achieve or exceed objectives
4. Schedule: a plan showing when individual or group activities or accomplishments will be started and/or completed
5. Budget: planned expenditures required to achieve or exceed objectives
6. Forecast: a projection of what will happen by a certain time
7. Organization: design of the number and kinds of positions, along with corresponding duties and responsibilities, required to achieve or exceed objectives
8. Policy: a general guide for decision-making and individual actions
9. Procedure: a detailed method for carrying out a policy
10. Standard: a level of individual or group performance defined as adequate or acceptable.

## Slide 8: Life Cycle Phases for Project Management

## Slide 9: Project Management Lifecycle Planning
Conceptualisation
Feasibility
Preliminary Planning
Detail Planning
Execution
Testing and Commissioning
Project planning provides for a uniform approach to project management across the organisation. Project managers still maintain ultimate control, however the project organisation may define key stage gates that must be complied with before allowing the project to proceed into the next stage.
Key decisions at the end of each stage may include:
  ● Proceed with the next phase based on an approved funding level
  ● Proceed to the next phase but with a new or modified set of objectives
  ● Postpone approval to proceed based on a need for additional information
  ● Terminate project
Concept Document
Prefeasibility Report
Feasibility Report
High level project plan
Cost/Benefit Analysis
Scope of Work
Contractor task
Specifications
Objectives
Detailed project plan
Work Breakdown Structure
Detailed specifications
Milestone schedule
Project Schedule
Project meeting reports
Issue and Risk Log
Schedule of performance
Test Plan
Snag List
Handover Plan
Close out report

## Slide 10: Important documents in project planning
Effective total program planning cannot be accomplished unless all of the necessary information becomes available at project initiation. These information requirements are:
Statement of Work
Project Specifications
Milestone Schedule
Work Breakdown Structure
The statement of work (SOW) is a narrative description of the work to be accomplished. It includes the objectives of the project, a brief description of the work, the funding constraint if one exists, and the specifications and schedule. It includes such things as the:
● Start date
● End date
● Major milestones
● Written reports (data items)
There are four elements of scope:
 Scope: This is the summary of all the deliverables required for the project, such as products, services and results.
 Project Scope: This entails work that must be completed in order to achieve the final scope of the project such as products, services and end results.
 Scope Statement: The purpose of the document is to ensure that all stakeholders have common knowledge of the project scope. The scope statement contains the objectives, description of deliverables, end results and justification of the project.
 Statement of work: This is a description that narrate the end results to be provided under the contract.

## Slide 11: Important documents in project planning
Effective total program planning cannot be accomplished unless all of the necessary information becomes available at project initiation. These information requirements are:
Statement of Work
Project Specifications
Milestone Schedule
Work Breakdown Structure
Specifications are used for man-hour, equipment, and material estimates. Another reason for identifying the specifications is to make sure that there are no surprises for the customer downstream.
Specifications are, in fact, standards for pricing out a proposal. If specifications do not exist or are not necessary, then work standards should be included in the proposal.
Eg.
Description | Specification No
Civil Engineering | 100
Concrete | 101
Electrical | 102
Roofing | 103
Structural | 104
Piling | 105

## Slide 12: Important documents in project planning
Effective total program planning cannot be accomplished unless all of the necessary information becomes available at project initiation. These information requirements are:
Statement of Work
Project Specifications
Milestone Schedule
Work Breakdown Structure
All project milestone schedules must contain information such as:
 Project Start Date
 Project End Date
 Data items (deliverables or reports)
Project start and end dates, if known, must be included. Other major milestones, such as review meetings, prototype available, procurement, testing, and so on, should also be identified. Data items, are often overlooked. There are two good reasons for preparing a separate schedule for data items. First, the separate schedule will indicate to line managers that personnel with writing skills may have to be assigned. Second, data items require direct-labor man-hours for writing, typing, editing, retyping, proofing, graphic arts, and reproduction.

## Slide 13: Important documents in project planning
Effective total program planning cannot be accomplished unless all of the necessary information becomes available at project initiation. These information requirements are:
Statement of Work
Project Specifications
Milestone Schedule
Work Breakdown Structure
The WBS is the single most important element because it provides a common framework from which:
● The total program can be described as a summation of subdivided elements.
● Planning can be performed.
● Costs and budgets can be established.
● Time, cost, and performance can be tracked.
● Objectives can be linked to company resources in a logical manner.
● Schedules and status-reporting procedures can be established.
● Network construction and control planning can be initiated.
● The responsibility assignments for each element can be established.